## Service Virtualization
The purpose of this document is to provide a high level plan for upgrading Service Virtualization, with some of best practices which customer should follow to help with a successful upgrade.
Introduction Activities
Planning/Prerequisite Activities | Comments | Due Date | Start Date | End Date
Environment: | The environment that you plan to upgrade, such as Production, Developmen, or QA
Type of Upgrade: | What type of upgrade
Type of Service Virtualization Installation: | How the Service Virtualization is going to be installed
Existing Service Virtualization Servers Information | Details of the Service Virtualization Server Install. How many environments and how all the Service Virtualization components IAM, Enterprise Dashboard, Registry, Broker, Portal, VSE, VSC, Coordinator and Simulator are distributed. Please provide the details for each environment. You need to document any Integration connection properties or any customizations prior to upgrading.
What Service Virtualization Features are you using:
Featues used in the current version of Service Virtualization
Component Integrations: | Any third party component integrations.
Additional Customizations:
Upgrade Purpose | Comments | Due Date | Start Date | End Date
Current version of Service Virtualization: | What is your current version of Service Virtualization?
Upgrade version of Service Virtualization: | What version of Service Virtualization are you upgrading to?
Reason for the Upgrade: | Why are you upgrading? What are you wanting to accomplish by upgrading?
Identity Access Manager Server Details | Comments | Due Date | Start Date | End Date
Hostname: | Identity Access Manager server details
RAM:
CPU:
OS Platform:
Customizations:
Patches:
SSL Configuration details:
Enterprise Dashboard Server Details | Comments | Due Date | Start Date | End Date
Hostname: | Enterprise Dashboard Server details
RAM:
CPU:
OS Platform:
Customizations:
Patches:
SSL Configuration details:
Registry & Broker Server Details | Comments | Due Date | Start Date | End Date
Hostname: | Registry and Broker Server details
RAM:
CPU:
OS Platform:
Customizations:
Patches:
SSL Configuration details:
Portal Server Details | Comments | Due Date | Start Date | End Date
Hostname: | Portal server details
RAM:
CPU:
OS Platform:
Patches:
SSL Configuration details:
VSE Server Details | Comments | Due Date | Start Date | End Date
Hostname: | VSE Server details
RAM:
CPU:
OS Platform:
Customizations:
Patches:
SSL Configuration details:
Coordinator Server Details | Comments | Due Date | Start Date | End Date
Hostname: | Coordinator Server details
RAM:
CPU:
OS Platform:
Customizations:
Patches:
SSL Configuration details:
Simulator Server Details | Comments | Due Date | Start Date | End Date
Hostname: | Simulator Server details
RAM:
CPU:
OS Platform:
Customizations:
Patches:
Virtual Service Catalog Server Details | Comments | Due Date | Start Date | End Date
Hostname: | Virtual Service Catalog Server details
RAM:
CPU:
OS Platform:
Customizations:
Patches:
Service Virtualization Workstation Details | Comments | Due Date | Start Date | End Date
Hostname: | Details of the Service Virtualization Workstation Install.
RAM:
CPU:
OS Platform:
Service Virtualization version:
Integrations:
Service Virtualization Databases Details
Identity Access Manager Database Server Details | Comments | Due Date | Start Date | End Date
Hostname: | Details of the Service Virtualization Databases configured for Identity Access Manager(IAM), Enterprise Dashboard(ED) and Registry.
Database Platform: | SQL Server, Oracle, etc.
Database version:
Communication Port:
RAM:
CPU:
OS Platform:
Existing or New?: | NOTE: Credentials used for the database connections should have full permissions.
Enterprise Dashboard Database Server Details | Comments | Due Date | Start Date | End Date
Hostname: | Details of the Service Virtualization Databass configured for Enterprise Dashboard (ED)
Database Platform: | SQL Server, Oracle, etc.
Database version:
Communication Port:
RAM:
CPU:
OS Platform:
Existing or New?: | NOTE: Credentials used for the database connections should have full permissions.
Registry Database Server Details | Comments | Due Date | Start Date | End Date
Hostname: | Details of the Service Virtualization Database configured for Registry.
Database Platform: | SQL Server, Oracle, etc.
Database version:
Communication Port:
RAM:
CPU:
OS Platform:
Existing or New?: | NOTE: Credentials used for the database connections should have full permissions.
Pre-Upgrade Activities | Comments | Due Date | Start Date | End Date
1. Snapshot of your Service Virtualization environment | Service Virtualization provides ServiceManger tool to captur the snap shot of the Registry server. This snapshot will collect the files of different components connected to the Registry. Please look at the knowledge article https://ca-broadcomcsm.wolkenservicedesk.com/wolken/esd/knowledgebase_search?articleId=99186 for capturing the snapshot.
2. Backup Service Virtualization Databases | If you are using the existing databses for IAM, ED and Registry then take a backup of the databases. If you are going to use new databses then you are ok.
3. Backup Service Virtualization Install and Data folders | If you are planning to install Service Virtualization into new folder then you are ok but if you are doing inplace upgrade, then take a backup of the install folder and data folderis must. This is a mandatory step that needs to be done prior to proceeding with the upgrade. We will be doing an in place upgrade which necessitates to back up the following to a remote location: • The entire existing Service Virtualization 10.0 folder. This would take care of the following which are important files in your installation • Properties files (local, site, lisa and dradis) • Virtual Services (if stored locally) • Application Test tests (if stored locally) • HotDeploy folder • vseDeploy folder • lib • any custom folders If you have stored your existing Tests and Virtual Services in a Source Control Repository, then the recommendation is to make a copy of those assets. Once that copy is created, you can use the new copy with Service Virtualization 10.x. In this case, if there are any issues, then you would have a backup to fall back on if required. NOTE: All the above files and folders are preserved during the upgrade from the previous release. The backup is precautionary if there was to be an unforeseen issue during the in-place upgrade. Always back up existing projects, properties files, etc. even if you are using a versioning system.
4. Service Virtualization Licenses | You need a new Service Virtualization license based on the version of Service Virtualization you are using and upgrading to. Please look at the 10.6 License Administration documentation at https://techdocs.broadcom.com/us/en/ca-enterprise-software/devops/Service Virtualization-solutions/10-6/administering/license-administration.html for more information. Make sure you have a valid license.
5. Review the information Preupgrade | • Preparing Your Service Virtualization Upgrade: https://techdocs.broadcom.com/us/en/ca-enterprise-software/devops/Service Virtualization-solutions/10-6/installing/preparing-your-Service Virtualization-upgrade.html • Preparing for Upgrade to Service Virtualization 10.6.0: https://knowledge.broadcom.com/external/article?articleId=187023 • Service Virtualization Upgrade Center: https://community.broadcom.com/communities/community-home/librarydocuments/viewdocument?DocumentKey=90296137-449c-4bab-856c-4b6eab36bde4 • System Requirements: Please look at the 10.6 documentation at https://techdocs.broadcom.com/us/en/ca-enterprise-software/devops/Service Virtualization-solutions/10-6/installing/preinstallation/system-requirements.html and make sure all the requirements are met. Service Virtualization 10.6 Release Notes: https://techdocs.broadcom.com/us/en/ca-enterprise-software/devops/Service Virtualization-solutions/10-6/release-notes.html
6. Download Service Virtualization Installer | Download the appropriate Service Virtualization installers from https://support.broadcom.com and select the product Service Virtualization and select the installer for your operating System. Please look at the documentation https://techdocs.broadcom.com/us/en/ca-enterprise-software/devops/Service Virtualization-solutions/10-6/installing/preinstallation/download-Service Virtualization-solutions-installers.html#concept.dita_85f4a805c28457c0a516d1aa2de67f5598b6cce0 for downloading the installer.
Upgrade Activities for Service Virtualization
Service Virtualization Server Upgrade | Comments | Due Date | Start Date | End Date
1. Stop Service Virtualization Services | Shutdown the following component services (if your existing Service Virtualization runs as services/server) in addition to Service Virtualization UIs, Workstation or Demoserver. This is also applicable for the various components installed remotely that connect to the Registry. • Service Virtualization Identity Access Manager • Service Virtualization Enterprise Dashboard • Service Virtualization Registry Service • Service Virtualization Coordinator Service • Service Virtualization Simulator Service • Service Virtualization VSE Service • Service Virtualization Portal Service • Service Virtualization Broker Service
2. Installing and Configuring Service Virtualization Server & Workstation | Extract the installation zip files downloaded previously and launch the Service Virtualization installation utility to start the upgrade process for the server. • Installing and Configuring Service Virtualization Server: Look at the documentation at https://techdocs.broadcom.com/us/en/ca-enterprise-software/devops/Service Virtualization-solutions/10-6/installing/installing-and-configuring-Service Virtualization-server.html which provides the steps to follow for installing Service Virtualization on Windows, UNIX and OS X operating ssystems. • Installing Service Virtualization Workstation: Look at the documentation at https://techdocs.broadcom.com/us/en/ca-enterprise-software/devops/Service Virtualization-solutions/10-6/installing/installing-Service Virtualization-workstation.html for installing Service Virtualization Workstation on Windows and OS X.
Verify the Server Upgrade | Comments | Due Date | Start Date | End Date
1. Start the Service Virtualization Services | After installation, start the Service Virtualization services in this order: 1. Identity and Access Manager 2. Enterprise Dashboard 3. Registry 4. Portal 5. Broker 6. Coordinator 7. Simulator 8. VSE Look at the documentation https://techdocs.broadcom.com/us/en/ca-enterprise-software/devops/Service Virtualization-solutions/10-6/installing/verifying-the-Service Virtualization-installation.html for starting the Service Virtualization services.
2. Verify the Identity Access Manager status | https://localhost:51111/ will show the UI (login) for Identity Access Manager. Verify if you can login to the IAM UI using admin user. Once you login, you can perform user and role management and configure active directory / ldap integration (if desired). NOTE: localhost is the name of the server where IAM is running.
3. Verify Enterprise Dashboard status | http://localhost:1506 should show the new UI (login) for Enterprise Dashboard. You can log into the Enterprise Dashboard with the same admin user that you use with portal. Note: Before you bring up the Enterprise Dashboard UI, be sure to clear your browser cache. NOTE: localhost is the name of the server where ED is running.
4. Verify the Portal status | http://localhost:1507/Service Virtualization should show the UI for P{ortal. Since this is the first time Service Virtualization is starting, give it about five minutes to load the various components, then verify that you can log in to the Service Virtualization Portal as admin user. NOTE: localhost is the name of the server where PORTAL is running.
5. Verify the logs | Verify that the lisatmp_10.x.x folder is created. This is if Service Virtualization is started as Windows services. If started as regular application from command line lisatmp_10.x.x is under %USERS%\<user>. NOTE: X refers to the Service Virtualization version.
Post Upgrade Activities for Service Virtualization
Service Virtualization Post Upgrade Tasks | Comments | Due Date | Start Date | End Date
1. Property Files | It is highly recommended that you review the properties files after the upgrade to confirm all settings have been preserved. Some properties and properties files change during the upgrade and may need to be manually updated. • If you created a local.properties file, the file is preserved as is. • If you created a site.properties file, the file is preserved as is. • A default _dradis.properties file is created. Any customized properties for Enterprise Dashboard in your local.properties or site.properties file are migrated to a dradis.properties file. • The default _local.properties file of the existing installation is replaced with the 10.6 version. • The default _site.properties file of the existing installation is replaced with the 10.6 version. • The lisa.properties file of the existing installation is replaced with the 10.6 version. You should never modify the lisa.properties file. If you did make changes to the lisa.properties file, the upgrade process overwrites the changes. You should move those changes to site.properties or local.properties before the upgrade. Always verify the out-of-the-box settings before adding in external database and security configurations. Properties files are evaluated in the following order: • lisa.properties • site.properties (take precedence over lisa.properties) • local.properties (takes precedence over site.properties and lisa.properties) • Command line and vmoptions files (takes precedence over all properties defined in any of the properties files)
2. Custom Folders | If the existing installation contains any custom folders, the folders are preserved as is.
3. Custom JAR Files | If the existing installation contains any custom JAR files in the <LISA_HOME>\lib directory, the JAR files are reserved as is.
4. Memory Allocation Settings | If the existing installation contains any modified ‘.vmoptions’ files in the <LISA_HOME>\bin directory, the files are preserved as is.
5. Projects | The Projects directory will be deleted. Save your Projects directory outside the <Service Virtualization_HOME> directory (e.g. \Service Virtualization_Projects_Backup).
6. Access Control and LDAP Configuration | Access Control and LDAP configuration has now been moved to Identity and Access Manager. All access related configurations need to be done through IAM UI. The documentation is available at https://techdocs.broadcom.com/us/en/ca-enterprise-software/devops/Service Virtualization-solutions/10-6/administering/security/identity-and-access-manager.html
Application Test
Virtual Service Environment
Continuous Application Insight
Performance Testing
Functional Testing
Virtual Service Catalog
APIs
Plugins
Other
In-place
New
Automatic
Silent
Manual
Third Party Jars
Customizations
List of Patches
Other
Existing
New
Existing
New
Existing
New
Other
AD/LDAP
CA Signed Certificats
TDM
Blazemeter
HP ALM
Third Party Jars